## Project BACKLOG
Task Number | Due Date | On Time? | Task Description
1 |  |  | Review ATSAMD20 dev kit | SPRINT 1
2 |  |  | Setup Ide Enviroment for firmware (Microchip Studio) | ¦
3 |  |  | Led blink using Dev Board | ¦
4 |  |  | Interface devboard ENC28J60 | ¦
5 |  |  | Interface with devboard's ATWINC1500 | ¦
6 |  |  | Simulate using Wink card to communicate with a network on dev board | ¦
7 |  |  | Simulate using ENC card to cummunicate with network on dev board | ¦
8 |  |  | Design a Power Source | ¦
9 |  |  | Solder Power Circuit | ¦
10 |  |  | Test Power Sources | ¦
11 |  |  | Add ATSAMD20E18 to circuit | ¦
12 |  |  | Add ENC28J60to circuit | ¦
13 |  |  | Add ATWINC1500 circuit | ¦
14 |  |  | Add LED(status code) circuit | ¦
15 |  |  | Research communication circuit(how to upload firmware to a microcontroller) | ¦
16 |  |  | Implement communication port to hardware prototype | ¦
17 |  |  | Upload firmware to prototype for the first time(blink led) | ¦
18 |  |  | Research Ultrasonic sensors | ¦
19 |  |  | Research how to read gear revolutions/ultrasonic readings to calculate flow | ¦
20 |  |  | Create alpha-prototype of ultrasonic sensor | ¦
21 |  |  | Setup Ide Enviroment for backend(hw server) PhpStorm | SPRINT 2
22 |  |  | Research AWS MQTT | ¦
23 |  |  | Create AWS EC2 instance for hardware data proccessing(MQTT protocol) | ¦
24 |  |  | Design hardware data database | ¦
25 |  |  | Create AWS RDS for hardware data to proccess | ¦
26 |  |  | Create AWS EC2 instance for frontend and backend server | ¦
27 |  |  | Create AWS RDS for hardware derived data | ¦
28 |  |  | Design and implement AWS Route53 | ¦
29 |  |  | Research apache security and routing | ¦
30 |  |  | Configure apache for security | ¦
31 |  |  | Create Crud/Gsad model to work with data | ¦
32 |  |  | Interface prototype sensor with dev board | ¦
33 |  |  | Finalize sensor design | ¦
34 |  |  | Send MQTT request using Dev board | ¦
35 |  |  | Research Local webserver for device | ¦
36 |  |  | Implement Local webserver on Dev board | ¦
37 |  |  | Research sensor reading circuit | ¦
38 |  |  | Design sensor reading circuit | ¦
39 |  |  | Implement sensor reading circuit on dev board | ¦
40 |  |  | Collect data using sensor on dev board and send to server | ¦
41 |  |  | Build final sensor(s) | SPRINT 3
42 |  |  | Build sensor(s) reading circuit on hardware prototype | ¦
43 |  |  | Collect data using sensor on hardware prototype and send to server | ¦
44 |  |  | Design final pcb layout | ¦
45 |  |  | Build Pcb | ¦
46 |  |  | Design plastic enclosure | ¦
47 |  |  | Build/order enclosure | ¦
48 |  |  | Assemble final product | ¦
49 |  |  | Setup Ide Enviroment for frontend(client). Phpstorm/Visual Studios | ¦
50 |  |  | Design basic html/css layout of client | ¦
51 |  |  | Communicate with backend to request data | ¦
52 |  |  | Present 'realtime' data to the server | ¦
53 |  |  | Extra stuff? | ¦

## Sprint1
| Task | Start Hours | Hours Spent: Day 28 | Hours Spent: Day 27 | Hours Spent: Day 26 | Hours Spent: Day 25 | Hours Spent: Day 24 | Hours Spent: Day 23 | Hours Spent: Day 22 | Hours Spent: Day 21 | Hours Spent: Day 20 | Hours Spent: Day 19 | Hours Spent: Day 18 | Hours Spent: Day 17 | Hours Spent: Day 16 | Hours Spent: Day 15 | Hours Spent: Day 14 | Hours Spent: Day 13 | Hours Spent: Day 12 | Hours Spent: Day 11 | Hours Spent: Day 10 | Hours Spent: Day 9 | Hours Spent: Day 8 | Hours Spent: Day 7 | Hours Spent: Day 6 | Hours Spent: Day 5 | Hours Spen: t Day 4 | Hours Spent: Day 3 | Hours Spent: Day 2 | Hours Spent: Day 1 | Total Hours
1 | Review ATSAMD20 dev kit | 6 | [28 empty] | 0
2 | Setup Ide Enviroment for firmware (Microchip Studio) | 4 | [28 empty] | 0
3 | Led blink using Dev Board | 2 | [28 empty] | 0
4 | Interface devboard ENC28J60 | 8 | [28 empty] | 0
5 | Interface with devboard's ATWINC1500 | 8 | [28 empty] | 0
6 | Simulate using Wink card to communicate with a network on dev board | 4 | [28 empty] | 0
7 | Simulate using ENC card to cummunicate with network on dev board | 4 | [28 empty] | 0
8 | Design a Power Source | 8 | [28 empty] | 0
9 | Solder Power Circuit | 4 | [28 empty] | 0
10 | Test Power Sources | 2 | [28 empty] | 0
11 | Add ATSAMD20E18 to circuit | 6 | [28 empty] | 0
12 | Add ENC28J60to circuit | 6 | [28 empty] | 0
13 | Add ATWINC1500 circuit | 6 | [28 empty] | 0
14 | Add LED(status code) circuit | 2 | [28 empty] | 0
15 | Research communication circuit(how to upload firmware to a microcontroller) | 5 | [28 empty] | 0
16 | Implement communication port to hardware prototype | 5 | [28 empty] | 0
17 | Upload firmware to prototype for the first time(blink led) | 6 | [28 empty] | 0
18 | Research Ultrasonic sensors | 25 | [28 empty] | 0
19 | Research how to read gear revolutions/ultrasonic readings to calculate flow | 6 | [28 empty] | 0
20 | Create alpha-prototype of ultrasonic sensor | 9 | [28 empty] | 0
| Actual Remaining Hours | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126
| Estimated Remaining Hours | 126 | 121.5 | 117 | 112.5 | 108 | 103.5 | 99 | 94.5 | 90 | 85.5 | 81 | 76.5 | 72 | 67.5 | 63 | 58.5 | 54 | 49.5 | 45 | 40.5 | 36 | 31.5 | 27 | 22.5 | 18 | 13.5 | 9 | 4.5 | 0
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: January 13th Begins SPRINT 1
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: January 13th Begins SPRINT 1
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: January 13th Begins SPRINT 1
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: January 13th Begins SPRINT 1
Note on AE1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: END OF SPRINT: Feb. 14th

## Sprint2
| Task | Start Hours | Hours Spent: Day 25 | Hours Spent: Day 24 | Hours Spent: Day 23 | Hours Spent: Day 22 | Hours Spent: Day 21 | Hours Spent: Day 20 | Hours Spent: Day 19 | Hours Spent: Day 18 | Hours Spent: Day 17 | Hours Spent: Day 16 | Hours Spent: Day 15 | Hours Spent: Day 14 | Hours Spent: Day 13 | Hours Spent: Day 12 | Hours Spent: Day 11 | Hours Spent: Day 10 | Hours Spent: Day 9 | Hours Spent: Day 8 | Hours Spent: Day 7 | Hours Spent: Day 6 | Hours Spent: Day 5 | Hours Spen: t Day 4 | Hours Spent: Day 3 | Hours Spent: Day 2 | Hours Spent: Day 1 | Total Hours
1 | [27 empty] | 0
2 | [27 empty] | 0
3 | [27 empty] | 0
4 | [27 empty] | 0
5 | [27 empty] | 0
6 | [27 empty] | 0
7 | [27 empty] | 0
8 | [27 empty] | 0
9 | [27 empty] | 0
10 | [27 empty] | 0
11 | [27 empty] | 0
12 | [27 empty] | 0
13 | [27 empty] | 0
14 | [27 empty] | 0
15 | [27 empty] | 0
16 | [27 empty] | 0
17 | [27 empty] | 0
18 | [27 empty] | 0
| Actual Remaining Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimated Remaining Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sprint 2 Begins: February 14th

## Sprint3
| Task | Start Hours | Hours Spent: Day 25 | Hours Spent: Day 24 | Hours Spent: Day 23 | Hours Spent: Day 22 | Hours Spent: Day 21 | Hours Spent: Day 20 | Hours Spent: Day 19 | Hours Spent: Day 18 | Hours Spent: Day 17 | Hours Spent: Day 16 | Hours Spent: Day 15 | Hours Spent: Day 14 | Hours Spent: Day 13 | Hours Spent: Day 12 | Hours Spent: Day 11 | Hours Spent: Day 10 | Hours Spent: Day 9 | Hours Spent: Day 8 | Hours Spent: Day 7 | Hours Spent: Day 6 | Hours Spent: Day 5 | Hours Spen: t Day 4 | Hours Spent: Day 3 | Hours Spent: Day 2 | Hours Spent: Day 1 | Total Hours
1 | [27 empty] | 0
2 | [27 empty] | 0
3 | [27 empty] | 0
4 | [27 empty] | 0
5 | [27 empty] | 0
6 | [27 empty] | 0
7 | [27 empty] | 0
8 | [27 empty] | 0
9 | [27 empty] | 0
10 | [27 empty] | 0
11 | [27 empty] | 0
12 | [27 empty] | 0
13 | [27 empty] | 0
14 | [27 empty] | 0
15 | [27 empty] | 0
16 | [27 empty] | 0
17 | [27 empty] | 0
18 | [27 empty] | 0
| Actual Remaining Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimated Remaining Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sprint 2 Begins: February 14th

## SprintBurndown 1
Task | Decription | Owner: | Done?
1 | Review ATSAMD20 dev kit | Darren
2 | Setup Ide Enviroment for firmware (Microchip Studio) | Darren
3 | Led blink using Dev Board | Darren
4 | Interface devboard ENC28J60 | Darren
5 | Interface with devboard's ATWINC1500 | Darren
6 | Simulate using Wink card to communicate with a network on dev board | Darren
7 | Simulate using ENC card to cummunicate with network on dev board | Darren
8 | Design a Power Source | Austin
9 | Solder Power Circuit | Austin
10 | Test Power Sources | Austin
11 | Add ATSAMD20E18 to circuit | Austin
12 | Add ENC28J60to circuit | Austin
13 | Add ATWINC1500 circuit | Austin
14 | Add LED(status code) circuit | Austin
15 | Research communication circuit(how to upload firmware to a microcontroller) | Darren
16 | Implement communication port to hardware prototype | Darren
17 | Upload firmware to prototype for the first time(blink led) | Team
18 | Research Ultrasonic sensors | Carter
19 | Research how to read gear revolutions/ultrasonic readings to calculate flow | Carter
20 | Create alpha-prototype of ultrasonic sensor | Carter

## SprintBurndown 2
Task | Decription | Owner: | Done?

## SprintBurndown3
Task | Decription | Owner: | Done?